## Sheet1
Marine CoLABoration workplan 2016
|  | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Meetings | every meeting, one hour session reflection on learning, bring a project and discuss; relflection time; update projects around what we learnt; discussion on what worked and what didn’t, what we have learnt | LAB 3 March | MPA 1/2 day workshop ToC, Giles email diagnostic | LAB mtg - focus on values? |  | LAB mtg |  | LAB mtg - 2-day in Cornwall or Devon? |  | LAB mtg
Events |  | April: SUP-B hustings?; May: Mayoral election 5; Nov: Conference?
Opportunities |  | March: Plastic Funders mtg, Washington; June: CGF Trustee Mtg 7 June; Oct: CGF Trustee Mtg 25 Oct
Think [tank] | Learning exchange [own projects] [11] | March: Chagos (ZSL)
Horizon scanning
Values-based approach [4]
LABs/Movements/ Campaigns
Test [experiments] | Deliver SUP-B [8] | April: Hustings event?; May: London Mayor election
| Develop / Deliver Coastal / MPAs experiment [9] | March: Plan for half-day workshop agreed; April: Half-day workshop; June: Experiment 2 begins
| Develop experiment 3 [10] | June: Explore ideas for experiment 3
Learn [organisation-wide] | Strengthen buy-in (CEOs) | March: Dinner for CEOs
| Build links between other staff | April: ALL - Think space conversations within each organisation on people's time, room, resources
|  | Amy: Evaluation test questions on project plastics | Aniol: Explore what we have at NEF as changing behaviors through values based approach |  |  | All: identify volunteers, interns, PhD, experts | Giles: investigate learning support (NEF), PhD person, action learning PhD | Sue: Evaluation framework, tight brief questions | Heather: input, Marine MOOC using values
Share [rest of the world] | Framework to track impact / learning [12] | Oct: Case studies and communicate learning outwards
Comms value advisory
| Seminars / events | Nov: One-day conference on communicating the value of the ocean?
House keeping | Vision/Mission [1] | March: Finalised / agreed; April: Mirella/Amy: 1pg presentation/elevator pitch done; July: Mirella: Messages for communication, review what is required
| Governance [2] | March: Subgroup appt to advance governance doc; April: Mirella + all (Giles): using Louisa's Blue Print pull options and preferences, MOU + internal Governance; May: Giles: Review at May Governance document; June: Governance doc agreed
| Comms [3] | March: 1pg presentation / elevator pitch done; April: Louisa + Heather: comms outputs: webpage, documents? Dropbox
| Values-based' approach definition [4] | March: Subgroup appt to advance definition; draft shared for feedback; May: Sue: diagram,general definition with examples, diversity; June: Sue:Tom Crompton in May 1page
| ToC [5] | March: Subgroup appt to advance ToC; April: Giles: Rationale / skeleton shared for feedback; May: Via email: ToC agreed; June: TOC agreed
| Plan for post 2016 [6] | March: Aniol: Subgroup appt to advance LAB business plan; July: Business Plan done
| Funding proposal for post 2016 [7] | May: Aniol + Heather: Sub group appt to advance proposal; June: Sub group appt to advance proposal; Sept: Proposal ready; Oct: Proposal sent out